## Component B — Build
NBA Flask PWA — Component B: Software Build ¦ Apr 30 – Jul 1 2026
■ Completed |  | ■ In Progress |  | ■ Upcoming |  | ■ Stretch Goal
[6 empty] | APRIL 2025 | MAY 2025 | [30 empty] | JUNE 2025 | [29 empty] | JULY 2025
Phase | Task | Start | End | Status | Owner | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1
PLANNING | Identify real-world problem (sports data access) | 30 Apr 2025 | 03 May 2025 | ✓ Done | You
| Choose sports API & test endpoints | 30 Apr 2025 | 04 May 2025 | ✓ Done | You
| Define folder structure & boundaries | 01 May 2025 | 03 May 2025 | ✓ Done | You
BACKEND | Flask app scaffolding | 03 May 2025 | 07 May 2025 | ✓ Done | You
| API key env setup (.env / security) | 04 May 2025 | 05 May 2025 | ✓ Done | You
| Scores route & past events fetch | 05 May 2025 | 10 May 2025 | ✓ Done | You
| Upcoming games fetch | 07 May 2025 | 10 May 2025 | ✓ Done | You
| Teams route | 08 May 2025 | 11 May 2025 | ✓ Done | You
| Playoffs route | 12 May 2025 | 16 May 2025 | ✓ Done | You
| Bracket route | 14 May 2025 | 20 May 2025 | ✓ Done | You
FRONTEND | Base HTML templates | 05 May 2025 | 08 May 2025 | ✓ Done | You
| Shared nav component | 10 May 2025 | 12 May 2025 | ✓ Done | You
| Scores tab & day selector strip | 10 May 2025 | 16 May 2025 | ✓ Done | You
| CSS redesign | 14 May 2025 | 18 May 2025 | ✓ Done | You
| Playoffs standings page | 16 May 2025 | 20 May 2025 | ✓ Done | You
| Full bracket page (2025-26 live data) | 18 May 2025 | 28 May 2025 | ✓ Done | You
FEATURES | Box score modal on concluded game click | 28 May 2025 |  | ▶ Building | You
| NRL tab via TheSportsDB | 30 May 2025 |  | ▶ Building | You
| Team logo images |  |  | ○ To Do | You
| Favourite teams (IndexedDB persistence) |  |  | ○ To Do | You
SECURITY | User login / session (username + password) |  |  | ○ To Do | You
| Basic encryption of stored preferences |  |  | ○ To Do | You
INNOVATION | Prototype: AI game prediction widget (UI design) |  |  | ○ To Do | You
| Push notifications via FCM (stretch goal) |  |  | ○ To Do | You
TESTING | Unit testing — API fetch functions |  |  | ○ To Do | You
| Cross-browser testing (Chrome, Firefox, Safari) |  |  | ○ To Do | You
| Code optimisation (caching, lazy load) |  |  | ○ To Do | You
DEPLOY | PWA manifest & Workbox service worker |  |  | ○ To Do | You
| Version control tidy-up (GitHub commits) |  |  | ○ To Do | You
| Deploy to Vercel / Render (HTTPS) |  |  | ○ To Do | You
| Final QA & bug fixes |  |  | ○ To Do | You

## Component A — Documentation
NBA Flask PWA — Component A: Project Documentation ¦ Apr 30 – Jul 1 2026
■ Completed |  | ■ In Progress |  | ■ Upcoming |  | ■ Stretch Goal
[6 empty] | APRIL 2025 | MAY 2025 | [30 empty] | JUNE 2025 | [29 empty] | JULY 2025
Phase | Task | Start | End | Status | Owner | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1
1. IDENTIFYING | Define real-world problem & client need | 30 Apr 2025 | 04 May 2025 | ✓ Done | You
| Assess scheduling & financial feasibility | 30 Apr 2025 | 05 May 2025 | ✓ Done | You
| Generate functional & performance requirements | 01 May 2025 | 06 May 2025 | ✓ Done | You
| Define data structures & data types | 03 May 2025 | 07 May 2025 | ○ To Do | You
| Define project boundaries | 03 May 2025 | 07 May 2025 | ○ To Do | You
| Brainstorming / mind map / storyboard screenshots | 05 May 2025 | 10 May 2025 | ○ To Do | You
2. RESEARCH | Choose software development approach (Agile/Waterfall) | 05 May 2025 | 10 May 2025 | ○ To Do | You
| Gantt chart (scheduling & tracking) | 05 May 2025 | 10 May 2025 | ✓ Done | You
| Client correspondence — initial meeting notes | 01 May 2025 | 08 May 2025 | ○ To Do | You
| Client correspondence — progress check #1 | 20 May 2025 | 22 May 2025 | ○ To Do | You
| Client correspondence — progress check #2 | 10 Jun 2025 | 12 Jun 2025 | ○ To Do | You
| Data flow diagram (DFD) | 10 May 2025 | 16 May 2025 | ○ To Do | You
| Structure chart | 12 May 2025 | 18 May 2025 | ○ To Do | You
| Class diagram | 14 May 2025 | 20 May 2025 | ○ To Do | You
| Decision tree | 16 May 2025 | 22 May 2025 | ○ To Do | You
| Algorithm design documentation | 14 May 2025 | 22 May 2025 | ○ To Do | You
| Quality assurance criteria definition | 20 May 2025 | 26 May 2025 | ○ To Do | You
| Compliance & legislative requirements (Privacy Act) | 20 May 2025 | 26 May 2025 | ○ To Do | You
3. PRODUCING | Document algorithms (pseudocode / flowcharts) | 20 May 2025 | 05 Jun 2025 | ○ To Do | You
| Process diary — ongoing development log | 30 Apr 2025 | 01 Jul 2025 | ▶ Building | You
| Version control log (GitHub commit history) | 30 Apr 2025 | 01 Jul 2025 | ▶ Building | You
| Innovative solution prototype (UI wireframes) | 12 Jun 2025 | 20 Jun 2025 | ○ To Do | You
| Code generation screenshots | 05 May 2025 | 20 Jun 2025 | ▶ Building | You
4. TESTING | Define testing methodology (black/white box) | 16 Jun 2025 | 20 Jun 2025 | ○ To Do | You
| Test table — functional tests with results | 18 Jun 2025 | 24 Jun 2025 | ○ To Do | You
| Code optimisation technique documented | 20 Jun 2025 | 24 Jun 2025 | ○ To Do | You
| Evaluate software against requirements | 24 Jun 2025 | 28 Jun 2025 | ○ To Do | You
| Client feedback — final review session | 24 Jun 2025 | 26 Jun 2025 | ○ To Do | You
| Respond to feedback & document improvements | 26 Jun 2025 | 30 Jun 2025 | ○ To Do | You
C. PRESENTATION | Prepare 4-min presentation slides (PowerPoint) | 20 Jun 2025 | 27 Jun 2025 | ○ To Do | You
| Screenshots of development process for slides | 22 Jun 2025 | 27 Jun 2025 | ○ To Do | You
| Rehearse live software demo | 27 Jun 2025 | 30 Jun 2025 | ○ To Do | You
| Present to class + Q&A (Jul 1) | 01 Jul 2025 | 01 Jul 2025 | ○ To Do | You